YSGOL GOLWG Y CWM

School Development Plan

2025 – 2026

School Vision

Ysgol Golwg Y Cwm is an English medium, community focused school which serves the area of Penrhos and Ystradgynlais. Currently there are 202pupils on roll including a 3- and 4-year-old provision. The school also hosts a Flying Start setting and has 2 area Specialist Teaching Facilities for 20 pupils with ALN, who are drawn from other schools within the cluster. The school has a rolling 3-year average of approximately 32% of pupils who are eligible for FSM and 45% of children on the ALN register.

Ysgol Golwg y Cwm is a caring, happy, inclusive and stimulating learning community where our children feel safe and secure. Our wonderful school and our own woodland provide children with unique opportunities to achieve, develop confidence and self-esteem through learning and experiences both indoors and outdoors.

We provide a caring, happy and stimulating environment, where all our children feel safe and secure. We pride ourselves on the nurturing approach and the family feel as you walk through our school doors. Our dedicated and enthusiastic staff provide an exciting, creative and challenging curriculum and are committed to achieving the highest standards in teaching and learning for all children. A high priority is given to pupils’ personal, social and emotional development and we promote high standards of behaviour where children learn and play together. Children are at the heart of everything we do and we strongly believe that it is our role to ensure that all children reach their full potential whilst they are a member of our school family.

We strive to build positive relationships with our families and the community as it is our belief that we all need to work together for the best outcomes for our children.  Our dedicated family engagement officer is at hand to help, support and provide additional services if needed.

We are very fortunate to have wonderful school grounds and our own woods and the school is part of the Forest school initiative. This allows our children unique opportunities to achieve, develop confidence and self-esteem, through hands on learning experiences in our outdoor environment.

Working for Excellence – Children come First!

Gweithio I Ragoriaeth – Plant sy’n dod yn Gyntaf!

This document is based on the Welsh Government school improvement guidance, published June 2022

https://hwb.gov.wales/evaluation-improvement-and-accountability/school-improvement-guidance-framework-for-evaluation-improvement-and-accountability

| Timeline | Date | Staff Members and GB |
| --- | --- | --- |
| Planning | Summer 2025/Autumn 2025 | TH/HW |
| Reviewing | December 2025 | All staff |
| Reviewing | March 2026 | All staff |
| Reviewing | July 2026 | All staff |

| Contents | Page |
| --- | --- |
| Contextual information |  |
| School and Governing Body’s appraisal of progress with 20-20 priorities |  |
| School’s three-year priorities 2023 – 2026 |  |
| Priorities 2023 – 2024 |  |
| Checklist |  |

| Contextual Information |  |
| --- | --- |
| Workforce Planning: number of fte TEACHERS | 10.8 |
| Workforce Planning: number of fte SUPPORT STAFF | 12 |
| Pupil numbers and groups of learners |  |
| Grant funding plan (to include PDG, RCSIG, PL, Accelerated Learning) |  |
| Targets |  |
| Monitoring Evaluation and Review calendar |  |
| Professional Learning Plan | embed document here |

GROUPS OF CHILDREN – NUMBERS IN EACH YEAR GROUP 2025-2

| 2023-2024 | Pre school | Reception | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Eligible for Free School Meals |  | 4 | 5 | 7 | 15 | 13 | 9 | 7 | 60 |
| Focused RADY |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 14 |
| Child Protection CAFCASS Early Help Care and Support |  | 3 | 2 |  | 1 1 | 1 | 1 | 2 | 7 4 |
| Looked After Children Guardianship Adopted | 0 | 0 1 | 0 1 | 1 0 | 0 |  | 2 0 | 0 0 | 3 0 2 |
| English as an Additional Language * | 2 | 1 | 3 | 3 | 2 | 2 | 4 | 2 | 19 |
| MAT |  |  |  | 1 | 3 | 10 | 4 | 6 | 24 |
| Additional Learning Needs * |  |  |  |  |  |  |  |  |  |
| ULP |  | 4 | 1 | 0 | 0 | 0 | 2 | 1 | 8 |
| School IDP |  | 5 | 11 | 6 | 12 | 7 | 15 | 11 | 67 |
| LA IDP | 1 | 1 | 2 | 4 | 2 | 3 | 3 | 1 | 16 |
| Children going through D2D |  |  |  |  |  |  |  |  |  |
|  |  | 10 | 14 | 10 | 14 | 11 | 20 | 13 | =91 |
| Trauma |  | 7 | 11 | 8 | 6 | 14 | 18 | 11 | 75 |
| Disabled * |  |  |  |  |  | 1 | 1 | 1 | 3 |
| Young Carers |  |  |  |  | 1 | 1 |  |  | 2 |

Progress against previous inspection recommendations

| Very good progress | Strong progress | Satisfactory progress | Limited progress |
| --- | --- | --- | --- |
| Tackles the recommendation in every way | Tackles the recommendation on the whole | Tackles the recommendation in many ways | Does not satisfy the recommendation |
| Does not require any further attention to any aspect. Very good effect on the quality of provision. | Requires attention only to minor aspects. Positive effect on standards and / or the quality of provision. | Continues to require substantial attention to some important aspects. Limited effect on standards and / or quality of provision. | Each aspect or many important aspects continue(s) to require attention. No effect on standards and / or quality of provision. |

| Progress against previous Estyn Recommendations | Progress (choose colour) |
| --- | --- |
| Recommendation 1: To refine independent learning |  |
| Impact: |  |

School and Governing Body appraisal of the progress with 2023 / 2024 priorities

| Very good progress | Strong progress | Satisfactory progress | Limited progress |
| --- | --- | --- | --- |
| Tackles the recommendation in every way | Tackles the recommendation on the whole | Tackles the recommendation in many ways | Does not satisfy the recommendation |
| Does not require any further attention to any aspect. Very good effect on the quality of provision. | Requires attention only to minor aspects. Positive effect on standards and / or the quality of provision. | Continues to require substantial attention to some important aspects. Limited effect on standards and / or quality of provision. | Each aspect or many important aspects continue(s) to require attention. No effect on standards and / or quality of provision. |

| Progress against 2024 / 2025 priorities SEE IMPACT ASSESSMENTS - EMBEDDED | Progress (chose colour) | Carry forward to next year’s plan? |
| --- | --- | --- |
| Priority 1: Independent Learning |  |  |
| Success Criteria: |  |  |
| Impact: |  |  |
| Priority 2: RVE |  |  |
| Success Criteria: |  |  |
| Impact: |  | Good progress made |
| Priority 3: Cross cutting themes |  |  |
| Success Criteria: |  |  |
| Impact: |  |  |

Three-Year Priorities 2024 – 2025

|  | Learning and Teaching Experiences | Well-being, Care, Support and Guidance | Leading and Improving |
| --- | --- | --- | --- |
| 2025-2026 | - To improve the use of grammar, punctuation and spelling. - To improve numeracy across the curriculum. | To review and improve attendance procedures and strategies in order to improve attendance. | To review distributed leadership across all groups within the school in order to promote Innovation and Continuous Learning, improve Accountability and Decision-Making and enhance Collaboration and Communication |
| 2026-2027 | To review and refine curriculum provision to ensure skills coverage (LNF, DCF). To embed outdoor learning opportunities across the school. | To improve pupils’ ability to understand the thoughts and feelings of others and to be able to show greater empathy. | To ensure that the Governing Body have a positive role in ensuring progress in learning. |
| 2027-2028 | To maximise opportunities for outdoor learning experiences in order to ensure engagement and motivation to learn for all learners. To ensure progression and coverage of the RSE curriculum. | To review participation strategies and engage all stakeholders fully in the life of the school. | To review and refine leadership systems at all levels. |

|  | SIP Priority | Rationale | SLT Lead | Governor Link |
| --- | --- | --- | --- | --- |
| Priority 1: | To improve the use of grammar, punctuation and spelling. | Work trawl demonstrate that pupils need to focus on utilizing more accurate grammar, punctuation and spelling in their extended writing. | Alison Griffiths | Mathew Ace |
| Priority 2: | To improve numeracy across the curriculum. | Teacher evaluation and feedback indicates that they find it more difficult to incorporate Numeracy across the curriculum in planning and to offer authentic opportunities for learning. | Alison Griffiths | Matthew Ace |
| Priority 3: | To review and improve attendance procedures and strategies in order to improve attendance. | Attendance continues to prove cause for concern, particularly with specific cohorts of pupils. | Tracey Havard | Alison Griffiths |
| Priority 4: | To improve Oracy in Cymraeg across the school | Progress has been stagnant due to Cymraeg lead teacher leaving. The school needs to achieve the Gwobr Arian this year. | Tracey Havard | Cllr Williams |
| Priority 5: |  |  |  |  |

Year 1 Priorities

Priorities for 2025 – 2026

| Priority 1 To improve the use of grammar, punctuation and spelling. |  |  |  |  |  |  |  | Link to Estyn Inspection Area(s) - Learning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | SLT Priority Lead: AG |  |  |  |  |
| Success criteria: - Teaching Staff are able to plan effectively for the teaching of punctuation, grammar and spelling. - Teaching Staff have a sound understanding of progress in these areas. - Extended writing demonstrates a clear understanding and use of the effective use of grammar and punctuation at an appropriate level. - Spelling is plausible and mostly accurate in written work across all AOLEs. |  |  |  |  |  |  |  |  |  |  |  |  |
| Actions |  |  | Who? | By when? | Milestone Term 1 |  | Milestone Term 2 |  | Milestone Term 3 | Professional Development Needs (including LA support with number of planned days) |  | Source of Finance and Cost |
| 1. | Staff to undertake action research project to gain knowledge and understanding of best practice in teaching grammar and punctuation to different groups of learners. |  | DR, BS | Nov 25 | Research undertaken by Dec 25 |  | Action points from research practiced in class and fed back to other staff. By February 26 |  | Evaluation and feedback from project shared with all staff June 26 | Action research project |  | Supply cover to allow for this - 2 days x 4 people £1600 |
| 2, | To develop shared understanding of progression in the above skills. |  | DR and all staff | April 25 | Staff meeting to discuss progression – Nov 25 |  | Draft document produced Feb 26 |  | Final document produced and all staff have shared understanding |  |  | £200x 2 Supply cover for LLC lead |
| 3. | Marking and feedback to be clearly understood by staff. Ensure on going verbal feedback is utilized to address individual, group and class concerns in a timely and effective manner. |  | All staff | Oct 25 | Whole school expectations established. Oct 25 |  | Work scrutiny demonstrates progress. Feb 25 |  | Staff feedback of progress during progress reviews. June 26 |  |  | ADDS sessions – no cost implications Cover time for LLC lead to undertake work scrutiny. £200 |
| 4 | Collate portfolio of evidence detailing progression in writing with a focus on the above elements |  | DR | June 26 | Expectations for progression established Oct 25 |  | Evidence from first term gathered and discussed January 26 |  | Final portfolio produced June 26 |  |  | 2 days supply cover for LLC lead £400 |
| 5 | Ensure progress reviews include focus on the above elements |  | JH | Across the year | Progress review meetings indicate clear comments on SPaG. Oct 25 |  | Progress review meetings indicate clear comments on SPaG. Feb 26 |  | Progress review meetings indicate clear comments on SPaG. May 26 |  |  | ADDS time used for meetings – No cost |
| 6 | Monitoring through lesson observations, work scrutiny, and learning walk to ascertain progress. (Consider all groups of learners, eg. FSM, ALN ) |  | SMT | Ongoing | Work scrutiny undertaken and progress in learning in this area observed By Oct 25 |  | Lesson observation and learning walk undertaken. By Feb 26 |  | Work scrutiny undertaken and progress in learning observed By April 26. |  |  | EIG Grant – release time for SMT to monitor and report back. £800 |
| Termly progress report / impact assessment |  |  |  |  |  |  |  |  |  |  |  |  |
| Very good progress |  | Strong progress |  |  |  | Satisfactory progress |  |  |  |  | Limited progress |  |

Priorities for 2025 – 2026

| Priority 2 To improve numeracy across the curriculum. |  |  |  |  |  |  |  | Link to Estyn Inspection Area(s) - Learning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | SLT Priority Lead: AG |  |  |  |  |
| Success criteria: 1.Teaching Staff are able to plan effective opportunities for the teaching of numeracy across all AOLEs considering the needs of all learners. 2. There is a clear plan for numeracy opportunities for each progress step. 3. Nearly all pupils have made progress in numeracy according to teacher assessment/ snapshots. |  |  |  |  |  |  |  |  |  |  |  |  |
| Actions |  |  | Who? | By when? | Milestone Term 1 |  | Milestone Term 2 |  | Milestone Term 3 | Professional Development Needs (including LA support with number of planned days) |  | Source of Finance and Cost |
| 1. | Action research regarding numeracy teaching and opportunities |  | AG, NR | Dec 25 | Staff undertaken research project Dec 25 |  | Key messages disseminated and project underway Feb 26 |  | Overall evaluation of research project July 26 |  |  | £600 – PL |
| 2. | To ensure staff have access to appropriate resources. |  | AG | Throughout year | Review of relevant resources available for Numeracy teaching. Nov 25 |  | Gaps plugged Jan 26 |  | Review available resources to ensure suitability. June 26 |  |  | £500 |
| 4. | To ensure that all staff are planning for purposeful opportunities for Numeracy across the curriculum on a weekly basis. |  | All teaching staff | Throughout year | Planning scrutiny – medium term plans Nov 25 |  | Work scrutiny – evidence of weekly planning Jan 26 |  | Planning scrutiny March 26 |  |  | None HT/DHT to undertake |
| 5. | To increase the use of the outdoors and independent learning opportunities for Numeracy |  | AG | Throughout the year | Planning scrutiny to identify independent learning opportunities Nov 25 |  | Lesson observation- Numeracy including independent learning March 26 |  | Impact assessment June 26 |  |  | None |
| 6. | Produce a clear plan of numeracy across the curriculum opportunities for each class. |  | All teaching staff | Throughout year | Autumn term plan produced October 25 |  | Spring term plan produced Jan 26 |  | Summer term plan produced April 26 |  |  | None – ADDS sessions to be used |
| 7. | (Consider progress of all groups of learners and whether there has been any impact due to disadvantage, ALN etc.) |  | AG | Intermittently throughout year | work scrutiny Nov 25 |  | Lesson observation March 26 |  | Evaluate snapshots June 26 |  |  | Supply time to release AOLE lead to undertake monitoring. £800 EIG |
| Termly progress report / impact assessment |  |  |  |  |  |  |  |  |  |  |  |  |
| Very good progress |  | Strong progress |  |  |  | Satisfactory progress |  |  |  |  | Limited progress |  |
| Community Links: Use of local community for practical authentic learning experiences – shops etc. |  |  |  |  |  |  |  |  |  |  |  |  |

| Priority 3 To review and improve attendance procedures and strategies in order to improve attendance. |  |  |  |  |  |  |  | Link to Estyn Inspection Area(s) - Wellbeing, Care support and Guidance |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | SLT Priority Lead: T Havard |  |  |  |  |
| Success criteria: - Clear established procedures for identifying attendance concerns. - Improved awareness of the importance of attendance amongst staff and parents. - School based attendance group intervention established and improvements shown in attendance of targeted group. - Fewer children causing ongoing concern throughout the school. |  |  |  |  |  |  |  |  |  |  |  |  |
| Actions |  |  | Who? | By when? | Milestone Term 1 |  | Milestone Term 2 |  | Milestone Term 3 | Professional Development Needs (including LA support with number of planned days) |  | Source of Finance and Cost |
| 1. | Establish school working group for attendance to have oversight of developments and evaluation of progress. |  | TH/AC/NA/SG | Ongoing | Expectations established for group and initial meeting held. Oct 25 |  | Interim evaluation of actions implemented Feb 26 |  | Impact assessment of actions. June 26 |  |  | No cost implication |
| 2. | Ongoing evaluation of the attendance of all groups of learners including FSM, ALN, EAL |  | TH | Ongoing | Half term evaluation of different groups Oct 25 |  | Evaluation of interventions for different groups – targeted children Feb 26 |  | Overall impact assessment of attendance of different learners. | . |  | . |
| 3. | Establish weekly intervention group following the “Attendance Toolbook” programme with targeted groups of children. |  | AC | September 25 and ongoing | Expectations established for group and targeted children end Sept 25 |  | End of term evaluation of impact and new group established Jan 26 |  | End of year evaluation. |  |  | Rewards/ stickers etc £100 |
| 4. | Undertake action research on strategies to improve attendance |  | TH | From Sept 25 ongoing | Action research undertaken Oct 25 |  | Research project implemented Feb 26 |  | End of year evaluation, |  |  | Action research time |
| 5 | Ensure regular communication with parents/carers stressing the impact of poor attendance on learning and emotional wellbeing. |  | JH/TH | Ongoing | Initial letter out to parents Sept 25 |  | Children produced posters highlighting need for good attendance . Theses displayed around the school and sent home. Nov 25 |  | Evaluation of impact of this strategy on attendance. June 26 |  |  |  |
| Termly progress report / impact assessment |  |  |  |  |  |  |  |  |  |  |  |  |
| Very good progress |  | Strong progress |  |  |  | Satisfactory progress |  |  |  |  | Limited progress |  |
| Community Links: |  |  |  |  |  |  |  |  |  |  |  |  |

| Priority4 : Improve the use of Welsh across the school so that the school is accredited with the Cymraeg Campus Silver award. Key Question 1 Learning |  |  |  |  |  |  |  |  |  | Related to the: Learning |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | Success criteria in terms of standards or quality: - There is a shared and inclusive vision that shows a clear commitment to developing Welsh and Welshness at the school - All staff to engage in continuous professional learning and are aware of opportunities to develop their Welsh language skills in line with the Professional Standards and they reflect together on how to make their own learning more powerful - There is an established culture at the school where learners are actively encouraged to use Welsh - School leaders model head’s vision for Welsh at the school by actively using Welsh and promoting the Welsh culture and heritage. The school has an active Criw Cymraeg that are encouraged to proactively lead on the development of the Siarter Iaith. |  |  |  |  |  |  |
| Internal Accountability: CW SD |  |  |  | Accountability to the Governing Body: AG |  |  |  |  |  |  |  |  |  |  |  |  |
| Rationale for this priority The Siarter Iaith (Welsh Language Charter) is a national framework for all settings and schools to provide a holistic basis for planning experiences across the curriculum in order to increase learners’ use of Welsh and develop their confidence in the language. All schools, regardless of their linguistic nature, will work within the same Language Charter framework to achieve the aim of ensuring that learners: - are confident in using their Welsh language skills - foster positive attitudes towards the language - increase the use of the language inside and outside the school The principles set out in the Siarter Iaith are in keeping with the Curriculum for Wales 2022 guidance and the ‘Cymraeg 2050 Miliwn o Siaradwyr’ guidance. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Very good progress |  |  | Strong progress |  |  |  |  | Satisfactory progress |  |  |  |  |  | Limited progress |  |  |
| Actions |  |  |  |  | Who? |  | Milestone Term 1 |  | Milestone Term 2 |  |  | Milestone Term 3 | Professional Development Needs |  | Source of Finance and Cost |  |
|  | Re-establish the Criw Cymraeg initiative to ensure the school’s vision for Welsh has a high focus. The Criw Cymraeg will promote incidental Welsh and significantly improve the amount of Welsh spoken by both staff and pupils within the school. They will instil a genuine enthusiasm for the Welsh language and Welsh heritage ensuring that they become ethical, informed citizens who are ready to be citizens of Wales and the world. Key actions to include: - Fortnightly CC meetings to be held - CC to analyze data from the silver questionnaire, identify areas in need of improvement and inform all classes of the results (this could be done in a virtual assembly) - Welsh / Bilingual signage displayed inside and outside of school - Welsh displayed in all classrooms linked to current topic |  |  |  | Coordinator and Criw Cymraeg |  | 1.Learners from ks2 have been selected to be in ‘Criw Cymraeg’. Fortnightly meetings have been embedded. 2.Criw Cymraeg have studied and analysed the data from the silver questionnaire. They have informed all classes of the results and have identified key areas to develop. This could be done during the Welsh assembly. 3.Criw Cymraeg are beginning to develop bespoke Cymraeg Campus initiatives to increase the use of Welsh in the school and secure a strong Welsh ethos ensuring that they are becoming enterprising, creative contributors. |  | 1.Criw Cymraeg to use ideas from ‘Tanio’r Ddraig 2020’ to develop bespoke Cymraeg Campus initiatives to increase the use of Welsh in the school. 2.Most areas inside and outside of the school have Welsh / Bilingual signage. There is Welsh displayed in every classroom linked to current topic. All learners and staff are part of the school’s Cymraeg Campus journey and they understand the role of the Criw Cymraeg. They are kept informed of progress made and understand which areas need to be improved. Criw Cymraeg have made a presentation to the school SMT on their progress with the language charter. |  |  | Impact assessment on progress made. | Whole staff meetings / twilight sessions to share the vision for the Welsh language and identify any professional development needs and opportunities. Welsh co-ordinator to access online training with Athrawes Fro to evaluate impact of Silver Award targets |  | No cost Release time for the Welsh co-ordinator -£400 |  |
|  | Re-start the weekly/fortnightly Welsh assembly. Key actions to include: - Criw Cymraeg to lead the majority of the Welsh assembly - Children listening to Welsh songs. The resource ‘Fy Hoff Gân’ https://www.j2e.com/erw2/Gwenan+H/SDP++CYMRAEG+CAMPUS+SILVER/Teachers+Handbook+-+Fy+hoff+gan.pdf https://www.j2e.com/erw2/Gwenan+H/SDP++CYMRAEG+CAMPUS+SILVER/Fy+hoff+gan+-+Class+Resource.pptx can be used along with the ‘Tanio’r Ddraig’ resources https://www.j2e.com/erw2/Gwenan+H/SDP++CYMRAEG+CAMPUS+SILVER/Tanior+Ddraig+WELSH+MUSIC+Activity.pptx Criw Cymraeg introduce the bands/singers using the Welsh cards provided. - The assembly should also incorporate the reciting of a Welsh prayer, introduction of the Silver Award ‘Cwestiwn yr Wythnos’, the giving out of Welsh awards by the Criw Cymraeg. These activities will ensure that pupils are ethical, informed citizens and are healthy, confident individuals. |  |  |  |  |  | Weekly/Fortnightly Welsh assembly is embedded. Criw Cymraeg are successfully leading part of the Welsh assembly. Criw Cymraeg to model the ‘Cwestiwn yr Wythnos’ https://www.j2e.com/erw2/Gwenan+H/SDP++CYMRAEG+CAMPUS+SILVER/Cwestiwn+yr+Wythnos.pdf Headteacher and teaching staff greet and use basic Welsh commands during every assembly. The assembly has impacted on a greater awareness of the Welsh language across the school. Cwestiwn yr Wythnos is well established and many pupils are confidently using the ‘Cwestiwn yr Wythnos’. This has impacted the standards of incidental Welsh across the school and reinforces the teaching in the classroom. |  | Criw Cymraeg are beginning to lead the majority of Welsh Assembly. New traditional songs and hymns have been learned. This has enhanced pupils’ knowledge of Welsh culture. Criw Cymraeg introduce ‘Cwestiwn yr Wythnos’ and model how it can be used. Many pupils can confidently ask and answer ‘Cwestiwn yr Wythnos’. More able learners successfully use extended answers. This has impacted on the standards of Welsh oracy skills. |  |  | Criw Cymraeg are confident in their role in leading the majority of the Welsh assembly and they are successfully using an increasing range of language patterns. Nearly all learners can confidently ask and answer ‘Cwestiwn yr Wythnos’. More able learners are beginning to use ‘Cwestiwn yr Wythnos’ as a springboard to develop short conversations. Classes take it in turns to showcase short dramas, role plays, storytelling during the Welsh assembly |  |  |  |  |
|  | Increase the use of Welsh by pupils and staff ensuring plentiful opportunities for learners to use Welsh in various situations in and around school thus enabling them to communicate effectively in different forms and settings, through the medium of Welsh and English – Ambitious and Capable Learners. Key actions to include: - Establish a culture at the school where learners are actively encouraged to use Welsh. - Restart the initiatives set up for bronze award, i.e. ‘Cwestiwn yr Wythnos’, Helpwr Heddiw’, ‘Wal Graffiti’ and a take home Welsh initiative mascot. Each learner could use their own teddy/mascot/pet, uploading a photo and writing about their experiences in Welsh. Mascot help sheets: Fp: https://www.j2e.com/erw2/Gwenan+H/SDP++CYMRAEG+CAMPUS+SILVER/Welsh+Mascot+12.pptx 3&4, Soth Version: https://www.j2e.com/erw2/Gwenan+H/SDP++CYMRAEG+CAMPUS+SILVER/Welsh+Mascot+Help+34+SOUTH.pptx 3&4, North Version: https://www.j2e.com/erw2/Gwenan+H/SDP++CYMRAEG+CAMPUS+SILVER/Welsh+Mascot+Help+34+NORTH.pptx 5&6, South Version: https://www.j2e.com/erw2/Gwenan+H/SDP++CYMRAEG+CAMPUS+SILVER/Welsh+Mascot+Help+56+SOUTH.pptx 5&6, North Version: https://www.j2e.com/erw2/Gwenan+H/SDP++CYMRAEG+CAMPUS+SILVER/Welsh+Mascot+Help+56+NORTH.pptx - Criw Cymraeg to establish a hotspot e.g. Pod Siarad / Cornel Cloncan, during break times where learners are rewarded for holding a simple conversation in Welsh with a Criw Cymraeg member. |  |  |  |  |  | Begin to re-instate initiatives set up for the bronze award including ‘Cwestiwn yr Wythnos’, ‘Cymraeg ar dy Dafod’, ‘Helpwr Heddiw’, ‘Wal Graffiti’ and a take home Welsh initiative mascot. The silver ‘Cwestiwn yr Wythnos’ resource models differentiated answers - the more able learners are being challenged to use the more complex answers. All teaching staff and support staff take advantage of every opportunity to use incidental Welsh. Poster of popular Welsh apps ks2 and Fp shared with all learners: https://www.j2e.com/erw2/Gwenan+H/SDP++CYMRAEG+CAMPUS+SILVER/FP+Best+Welsh+apps+for+primary+sc https://www.j2e.com/erw2/Gwenan+H/SDP++CYMRAEG+CAMPUS+SILVER/ks2+Best+Welsh+apps+for+primary+school+pupils+April+2020+-+Copy.pdf Poster of popular Websites shared with all learners: https://www.j2e.com/erw2/Gwenan+H/SDP++CYMRAEG+CAMPUS+SILVER/Welsh+Websites+April+2020.pdf Most staff use the Welsh resources effectively to impact on the standards of Welsh across key stage 2. |  | The majority of the initiatives set up for bronze award, i.e. ‘Cwestiwn yr Wythnos’, ‘Cymraeg ar dy Dafod‘, Helpwr Heddiw’, ‘Wal Graffiti’ and a take home Welsh initiative mascot are embedded. Many learners are able to confidently recall and use previous questions introduced as ‘Cwestiwn yr Wythnos’. Most ks2 learners are using more challenging incidental Welsh phrases effectively when expressing need e.g. Ga i fenthyg…/Ga i nôl… /Ga i ddefnyddio… |  |  | All initiatives set up for bronze award are fully embedded. A hotspot e.g. Pod Siarad / Cornel Cloncan is being used regularly, during break times and most learners are holding a simple conversation in Welsh with a Criw Cymraeg member. There is an established culture at the school where all learners are actively encouraged to use Welsh. Many learners understand and respond to more complex Welsh questions and commands. |  |  |  |  |
|  | Learners to be given opportunities to develop their Welsh language skills across the curriculum ensuring they are able to communicate effectively in different forms and settings, through the medium of Welsh and English - Fp teachers to make use of the cross-curricular opportunities provided in the Powys Fp Welsh scheme of work and also the school developed powerpoint. - KS2 teachers to use cross curricular Welsh resources e.g. Athrawon Bro Powys resources as a tool for learning aspects of their topic work in Welsh. - An element of Welsh at an appropriate level to be visible on other classroom subject displays. - In all AoLE’s, learners to be given opportunities to evaluate their work at an appropriate level in Welsh, using familiar patterns |  |  |  |  |  | Teachers make good use of the cross-curricular opportunities provided in the Powys Fp Welsh scheme of work and GYC powerpoint KS2 teachers regularly use cross curricular Welsh resources e.g. Gwasanaeth Athrawon Bro Powys resources as a tool for learning aspects of their topic work in Welsh. An element of Welsh at an appropriate level is visible on other classroom subject displays. |  | There is evidence in books of learners evaluating their work at an appropriate level in Welsh, using familiar patterns e.g. Dw i’n meddwl bod… There is evidence of Welsh crosscurricular work undertaken in pupils’ topic workbooks. |  |  | Many learners to use Welsh effectively across the curriculum. Books viewed in staff meeting to share ideas and good practice. |  |  |  |  |
| How can the wider community of the school enrich the priority? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Invite visitors e.g. authors, singers, artists to lead workshops in the school - Arrange visits to various attractions in Wales |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MONITORING AND EVALUATIONS: Monitoring and evaluation will be conducted termly and will include activities such as listening to learners / wall trawl / learning walks. The strengths and areas for improvement will be collated by the Curriculum co-ordinator to produce a termly IMPACT ASSESSMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |